## Project Plans (2) (hidden)
Option 1 | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
| Date | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22
Initiate
Plan
Execute
Deliver
Close
B. Final Plan Post Workshops | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11
| Start Date | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12
Initiate | bar: 2025-10-27
Plan | bar: 2025-11-03 to 2025-11-17
Execute | bar: 2025-11-24 to 2025-12-15
Deliver | bar: 2025-12-22 to 2026-01-05
Close | bar: 2026-01-12

## Tasks and Estimates
| Phase | Start Week | End Week | Task | Description | Assumption | Hide Row from SOW | Practice | Presales Notes (Internal) | Billable/ Non-Billable | Role 1 | Role 2 | Role 3 | Role 4 | Role 5 | Role 6 | Role 7 | Role 8 | Role 9 | Role 10 | Role 11 | Role 12 | Role 13 | Role 14 | Role 15
Roles | Intentionally left blank. | Intentionally left blank. | Intentionally left blank. | Intentionally left blank. | Intentionally left blank. | Intentionally left blank. | Intentionally left blank. | Intentionally left blank. | Intentionally left blank. | Roles | Project Manager-PMO | Solution Architect-Technology | Business Process Consultant-Technology | Senior Technical Consultant-Technology | Workflow/Practice Strategist-Technology | - | - | - | - | - | - | - | - | - | -
| Initiate | 1 | 1 | Initiate Oversight & Calculated Hours | The calculated hours in the Initiate cover the project setup, onboarding of resources. It also covers an internal team kick-off, setting up the base project plan and conducting a formal project initiation with the customer to review goals, objectives, scope and other engagement information. |  |  |  |  | Billable | 10 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
Plan | Plan | 2 | 2 | Now Assist Agentic AI Workshop | [5 empty] | Billable | Role 2: 4; Role 3: 4; Role 5: 4 | 12
| Plan | 2 | 2 | Use Case Development |  | Time based, implementation is limited to up to 3 use cases |  |  |  | Billable | Role 2: 4; Role 3: 4; Role 5: 4 | 12
| Plan | 2 | 2 | Story Development and Review | [5 empty] | Billable | Role 2: 5; Role 3: 10 | 15
| Plan | 2 | 2 | Business Process Map Workshop (Use-Case Based) |  | Limited to the single use case identified from Use Case Dev above |  |  |  | Billable | Role 3: 4; Role 5: 4 | 8
| Plan | 2 | 2 | Now Assist Agentic AI Accelerator Pack | [5 empty] | Billable | [15 empty] | 0
| Plan | 2 | 2 | Boeing AI Roadmap Maturation Workshops | Review and update existing customer AI roadmap, including integration recommendations for 3rd party systems (moveworks for example) |  |  |  |  | Billable | Role 2: 8; Role 3: 8; Role 5: 10 | 26
| Plan | 2 | 2 | Value Realization Dashboard Workshop | Value realization dashboard use case development in support of AI Roadmap |  |  |  |  | Billable | Role 2: 4; Role 3: 4; Role 5: 8 | 16
| Plan | 2 | 2 | Integrations Evaluation and Recommendations Workshop | Review of existing Boeing 3rd party systems, such as Moveworks, and develop integration recommendations |  |  |  |  | Billable | Role 2: 4; Role 3: 4; Role 5: 4 | 12
| Plan | 2 | 2 | AI Governance Memo | Governance framework memo for AI | deliverable |  |  |  | Billable | Role 2: 2; Role 3: 2; Role 5: 2 | 6
| Plan | 2 | 2 | Plan Oversight & Calculated Hours | This covers any oversight necessary during the plan phase to coordinate meetings, schedule workshops, updating project plan, etc. In addition for the PM it covers the finalization of the Project Plan. |  |  |  |  | Billable | 10 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
| Plan | 2 | 2 | Workshop for Testing and Test Plan Document Creation |  |  |  |  | Remove this if the Testing package is not being sold | Billable | Role 15: 0 | 0
Execute | Execute | 3 | 6 | Now Assist Implementation - up to 3 use cases | Portal to include enhanced widgets, layout and functionality as determined during the design phase. Standard out of the box pages / functionality will be implemented for anything that was not enhanced during the design phase. | Limited to ITSM based on 50 licenses purchased for POC, halftime TC - 3 sprints |  |  |  | Billable | Role 4: 120 | 120
| Execute | 3 | 6 | Use Case Documentation | Business Case, ROI documentation creation |  |  |  |  | Billable | Role 3: 40 | 40
| Execute | 3 | 6 | Configuration Runbook Creation | Creation of configurations document to capture existin Now Assist config changes and NR AI Agent product configurations |  |  |  |  | Billable | Role 2: 4; Role 4: 4 | 8
| Execute | 3 | 6 | Execute Oversight & Calculated Hours | This covers the hours for the BA and/or SA to do the sprint demos, unit testing. Then for the PM it covers the oversight to manage the project during the Execute phase. |  |  |  |  | Billable | 40 | 32 | 32 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112
| Deliver | 7 | 7 | Training Preparation | Review training scope and the final content to be included in training based on the Deploy stage configurations. |  |  |  | Leave to 2 hours unless large engagement then increase to 4. | Billable | [15 empty] | 0
| Deliver | 7 | 7 | Create Training Materials | Up to 1 Quick Reference Guide included - Now Assist ITSM | • Training Materials will be limited to 1 Quick Reference Guide (QRG) • Training Materials will be in English and any other languages will be done by the Client |  |  | Adjust based on notes in Description: QRGs are correctly scoped unless the customer has a specific template they want to use. Add two hours. Alternative is to list the QRG as 8 to 10 hours for 3 to 4 pages of content. The PPT presentation is per application. Depending on the application, PPTs may take between 12 and 16 hours to complete. The Full Guide option should say 16 hours per application. Example: Incident Management Training Guide = 16 hours, Incident and Change Management = 32 hours, a full ITSM suite = 48 hours. Will need to add Video Demonstrations. Each video demonstration will be between 2 minutes and 8 minutes in length and cover individual topics. One hour should be allotted for every 5 minutes of video demo created. | Billable | [15 empty] | 0
| Deliver | 7 | 7 | Training Sessions | Perform Now Assist ITSm training for end-users. | • Trainings will be limited to 2 training sessions for each module (6 total hours) • Trainings will be done via Train the Trainer Method • Training will be done remotely • Training will be provided in English |  |  | Adjust based on notes in Description: PER APPLICATION: Onsite training up to 4 hours per application. Remote training up to 3 hours per application. | Billable | [15 empty] | 0
| Deliver | 7 | 7 | Deliver Oversight and UAT Support | The calculated hours in the Deliver phase cover the updating of user stories to reflect high-lvel test steps to validate functionality. This also covers demoing of the functionaliy to Client testers ahead of UAT, and supporting the UAT as a whole. In addition this includes the time it takes to migrate to UAT, creating a rollout plan, migrate to Production, as well as updating configuration documentation. |  |  |  |  | Billable | 10 | 8 | 4 | 20 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44
| Close | 8 | 8 | Close Oversight & Calculated Hours | The calculated hours in the Close phase cover the post-live support in a part-time capacity unless stated otherwise. It also covers a technical knowledge transfer session with the customer, a closeout meeting and the sending of the CSAT survey and updating of the deployment record. |  |  |  |  | Billable | 10 | 2 | 2 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26
Minimums | Initiate | 1 | 1 | Calculated Padding for minimums |  |  | Yes | Padding |  | Billable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Plan | 2 | 2 | Calculated Padding for minimums |  |  | Yes | Padding |  | Billable |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Execute | 3 | 6 | Calculated Padding for minimums |  |  | Yes | Padding |  | Billable |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Deliver | 7 | 7 | Calculated Padding for minimums |  |  | Yes | Padding |  | Billable |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Close | 8 | 8 | Calculated Padding for minimums |  |  | Yes | Padding |  | Billable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Roles and Skills | [5 empty] | OPTIONAL - Add Oversight | bar: Role 1 to Role 2
Roles and skills | Role # | Role + Practice | Resource Location | Practice | Skill #1 | Skill #2 | Skill #3 | Role | Initiate % | Initiate Hours | Role 1: Plan %; Role 2: Plan Hours; Role 3: Execute %; Role 4: Execute Hours; Role 5: Deliver %; Role 6: Deliver Hours; Role 7: Close %; Role 8: Close Hours
| Role 1 | Project Manager-PMO | USA | PMO |  |  |  | Project Manager |  | #REF! | Role 2: #REF!; Role 4: #REF!; Role 6: #REF!; Role 8: #REF!
| Role 2 | Solution Architect-Technology | USA | Technology | AI Now Assist ITSM |  |  | Solution Architect |  | #REF! | Role 2: #REF!; Role 4: #REF!; Role 6: #REF!; Role 8: #REF!
| Role 3 | Business Process Consultant-Technology | USA | Technology | AI Now Assist ITSM |  |  | Business Process Consultant |  | #REF! | Role 2: #REF!; Role 4: #REF!; Role 6: #REF!; Role 8: #REF!
| Role 4 | Senior Technical Consultant-Technology | India | Technology | AI Now Assist ITSM |  |  | Senior Technical Consultant |  | #REF! | Role 2: #REF!; Role 4: #REF!; Role 6: #REF!; Role 8: #REF!
| Role 5 | Workflow/Practice Strategist-Technology | USA | Technology | AI Now Assist ITSM |  |  | Workflow/Practice Strategist |  | #REF! | Role 2: #REF!; Role 4: #REF!; Role 6: #REF!; Role 8: #REF!
| Role 6 | - | [7 empty] | #REF! | Role 2: #REF!; Role 4: #REF!; Role 6: #REF!; Role 8: #REF!
| Role 7 | - | [7 empty] | #REF! | Role 2: #REF!; Role 4: #REF!; Role 6: #REF!; Role 8: #REF!
| Role 8 | - | [7 empty] | #REF! | Role 2: #REF!; Role 4: #REF!; Role 6: #REF!; Role 8: #REF!
| Role 9 | - | [7 empty] | #REF! | Role 2: #REF!; Role 4: #REF!; Role 6: #REF!; Role 8: #REF!
| Role 10 | - | [7 empty] | #REF! | Role 2: #REF!; Role 4: #REF!; Role 6: #REF!; Role 8: #REF!
| Role 11 | - | [7 empty] | #REF! | Role 2: #REF!; Role 4: #REF!; Role 6: #REF!; Role 8: #REF!
| Role 12 | - | [7 empty] | #REF! | Role 2: #REF!; Role 4: #REF!; Role 6: #REF!; Role 8: #REF!
| Role 13 | - | [7 empty] | #REF! | Role 2: #REF!; Role 4: #REF!; Role 6: #REF!; Role 8: #REF!
| Role 14 | - | [7 empty] | #REF! | Role 2: #REF!; Role 4: #REF!; Role 6: #REF!; Role 8: #REF!
| Role 15 | - | [7 empty] | #REF! | Role 2: #REF!; Role 4: #REF!; Role 6: #REF!; Role 8: #REF!
Scope & Assumptions | List Project Assumptions Here:
List Out of Scope Here:
Deliverables/Artifacts | Deliverable/ Artifact | Description |  |  | In Scope?
| Project Kick Off | NewRocket Kickoff PowerPoint |  |  | YES
| Status Reports | Weekly reports, which may include some, or all, of the following: |  |  | YES
| User Stories | All requirements collected throughout the Workshops documented in the Client’s Service Now instance. Describes in detail the customization needed to meet each requirement. |  |  | YES
| Unit Test Steps | Test steps prepared for each of the specifications and configurations in their respective story. |  |  | YES
| Configuration/Design Approach Document | End state documentation with all of the configuration completed by NewRocket |  |  | YES
| Rollout Plan | Step-by-step run book of go-live events |  |  | YES
| Training Materials | Quick Reference guides (QRG) for [modules] to support users post go-live |  |  | YES
Milestones | Milestone # | Trigger | % | Price
| Milestone 0 |  | 25% | 31250
| Milestone 1 |  | 25% | 31250
| Milestone 2 |  | 40% | 50000
| Milestone 3 |  | 10% | 12500
| Milestone 4 |  |  | 0
| Milestone 5 |  |  | 0
| Milestone 6 |  |  | 0
| Milestone 7 |  |  | 0
| Milestone 8 |  |  | 0
| Milestone 9 |  |  | 0
| Milestone 10 |  |  | 0
| Milestone 11 |  |  | 0
| Milestone 12 |  |  | 0
| Milestone 13 |  |  | 0
| Milestone 14 |  |  | 0
| Milestone 15 |  |  | 0
| Milestone 16 |  |  | 0
| Milestone 17 |  |  | 0
| Milestone 18 |  |  | 0
| Milestone 19 |  |  | 0
| Milestone 20 |  |  | 0
| Milestone 21 |  |  | 0
| Milestone 22 |  |  | 0
| Milestone 23 |  |  | 0
| Milestone 24 |  |  | 0
| Milestone 25 |  |  | 0
| Milestone 26 |  |  | 0
| Milestone 27 |  |  | 0
| Milestone 28 |  |  | 0
| Milestone 29 |  |  | 0
| Milestone 30 |  |  | 0 | Total from Pricing Tool. MUST MATCH
| Total |  | 100% | 125000 | 125000

## Deliverables
1 - NowAssist ITSM POC
Bundle | Deliverable | Description | Estimated Week
1.1 Discovery & Design | Project Workstream Kick-off Meeting | One (1) PowerPoint, review of SOW and alignment of project goals and outcomes | End of Week 2
| Now Assist ITSM Workshop | One (1) PowerPoint
| NewRocket Agentic Agent Workshop + NR Agents (Alara, Phoebe) | One (1) PowerPoint
1.2 POC Build & Demo | Now Assist ITSM Refinement | Now Assist configured in designed non-production environment, one (1) use case | End of Week 6
| NewRocket Agentic Agent Activation & Configuration | NewRocket Agentic Agent configured in designed non-production environment, up to two (2) agents
| NewRocket AI Value Realization Dashboard | One (1) snapshot dashboard with up to three (3) use cases specific to the POC
1.3 AI Strategy & Governance | AI Roadmap | One (1) AI roadmap | End of Week 7
| AI Integration Recommendations | One (1) Word (or agreed upon format) documenting integration recommendations with Boeing 3rd party systems
| AI Governance Memo | One (1) Word (or agreed upon format) AI Governance Memo document
1.4 Final Handover & Closeout | AI Configuration Runbook | One (1) Word (or agreed upon format) documenting configuration updates and NewRocket product configuration | End of Week 8
2 - Digital Product Release Advisory Services
Bundle | Deliverable | Description | Estimated Week
2.1 Discovery & Readout | Project Workstream Kick-off Meeting | One (1) PowerPoint, review of SOW and alignment of project goals and outcomes
| Release Management Workshops & Readout | One (1) PowerPoint
2.2 OCM Strategy Package | OCM Stakeholder Analysis and Impact Assessment | One (1) PowerPoint (or agreed upon format) | End of Week 4
| OCM Strategy | One (1) Word (or agreed upon format)

## Workshops
Workshop | Topics | Duration | Date | Lead
1 | Now Assist for ITSM Skills; Use Cases; Value Realization Dashboard Overview; Demo on Monitoring Assist Consumption; Boeing ITSM System features; Discussion + Draft Stories (outcome) | 2 hours | 2025-11-07 | Pankaj & Mylene
2 | Value Realization Dashboard Deep Dive | 1 hour | 2025-11-10 | Anusha & Mylene
3 | Demoing Phoebe and Elara (NR Agents); Stories refinement and sign off | 1.5 hours | 2025-11-11 | Anthony & Pankaj
4 | Boeing AI Roadmap Maturation; Integrations Evaluation and Recommendations | 1.5 hours | 2025-11-12 | Anusha
5 | Overflow sessions and follow-ups (As needed)

## Activities
| Phase | Start Week | End Week | Task | [6 empty] | Description | Assumption | Role 1 | Role 2 | Role 3 | Role 4 | Role 5
Roles | Intentionally left blank. | Intentionally left blank. | Intentionally left blank. | Intentionally left blank. |  |  | # of hours | Session 1 | Session 2 | Recommended Audience | Intentionally left blank. | Intentionally left blank. | Project Manager-PMO | Solution Architect-Technology | Business Process Consultant-Technology | Senior Technical Consultant-Technology | Workflow/Practice Strategist-Technology | # of Sessions | Session 1 | Session 2
| Initiate | 1 | 1 | Initiate Oversight & Calculated Hours | [6 empty] | The calculated hours in the Initiate cover the project setup, onboarding of resources. It also covers an internal team kick-off, setting up the base project plan and conducting a formal project initiation with the customer to review goals, objectives, scope and other engagement information. |  | 10 | 2 | 2 | 0 | 2
Plan | Plan | 2 | 3 | General | 1 | Now Assist for ITSM Skills; Use Cases; Value Realization Dashboard; Demo on Monitoring Assist Consumption; Boeing ITSM System features; Discussion + Draft Stories (outcome) | 2 hours | 2025-11-07 |  | ITSM Product Owner, ServiceNow Architect |  |  |  | 4 | 4 |  | 4
|  |  |  | Now Assist Agentic AI Workshop + Story Development and Review | 2 | Demoing Phoebe and Elara (NR Agents); Stories refinement and sign off | 1.5 hours | 2025-11-11
| Plan | 2 | 2 | Use Case Development | 3 | Boeing AI Roadmap Maturation; Integrations Evaluation and Recommendations | 1.5 hours | 2025-11-12 |  |  |  | Time based, implementation is limited to up to 3 use cases |  | 4 | 4 |  | 4
| Plan | 2 | 2 | Story Creation and Review | [9 empty] | 5 | 10
| Plan | 2 | 2 | Business Process Map Workshop (Use-Case Based) | [7 empty] | Limited to the single use case identified from Use Case Dev above |  |  | 4 |  | 4
| Plan | 2 | 2 | Boeing AI Roadmap Maturation Workshops | [6 empty] | Review and update existing customer AI roadmap, including integration recommendations for 3rd party systems (moveworks for example) |  |  | 8 | 8 |  | 10
| Plan | 2 | 2 | Value Realization Dashboard Workshop | [6 empty] | Value realization dashboard use case development in support of AI Roadmap |  |  | 4 | 4 |  | 8
| Plan | 2 | 2 | Integrations Evaluation and Recommendations Workshop | [6 empty] | Review of existing Boeing 3rd party systems, such as Moveworks, and develop integration recommendations |  |  | 4 | 4 |  | 4
| Plan | 2 | 2 | AI Governance Memo | [6 empty] | Governance framework memo for AI | deliverable |  | 2 | 2 |  | 2
| Plan | 2 | 2 | Plan Oversight & Calculated Hours | [6 empty] | This covers any oversight necessary during the plan phase to coordinate meetings, schedule workshops, updating project plan, etc. In addition for the PM it covers the finalization of the Project Plan. |  | 10 | 0 | 0 | 0 | 2
Execute | Execute | 3 | 6 | Now Assist Implementation - up to 3 use cases | [6 empty] | Portal to include enhanced widgets, layout and functionality as determined during the design phase. Standard out of the box pages / functionality will be implemented for anything that was not enhanced during the design phase. | Limited to ITSM based on 50 licenses purchased for POC, halftime TC - 3 sprints |  |  |  | 120
| Execute | 3 | 6 | Use Case Documentation | [6 empty] | Business Case, ROI documentation creation |  |  |  | 40
| Execute | 3 | 6 | Configuration Runbook Creation | [6 empty] | Creation of configurations document to capture existin Now Assist config changes and NR AI Agent product configurations |  |  | 4 |  | 4
| Execute | 3 | 6 | Execute Oversight & Calculated Hours | [6 empty] | This covers the hours for the BA and/or SA to do the sprint demos, unit testing. Then for the PM it covers the oversight to manage the project during the Execute phase. |  | 40 | 32 | 32 | 0 | 8
| Deliver | 7 | 7 | Deliver Oversight and UAT Support | [6 empty] | The calculated hours in the Deliver phase cover the updating of user stories to reflect high-lvel test steps to validate functionality. This also covers demoing of the functionaliy to Client testers ahead of UAT, and supporting the UAT as a whole. In addition this includes the time it takes to migrate to UAT, creating a rollout plan, migrate to Production, as well as updating configuration documentation. |  | 10 | 8 | 4 | 20 | 2
| Close | 8 | 8 | Close Oversight & Calculated Hours | [6 empty] | The calculated hours in the Close phase cover the post-live support in a part-time capacity unless stated otherwise. It also covers a technical knowledge transfer session with the customer, a closeout meeting and the sending of the CSAT survey and updating of the deployment record. |  | 10 | 2 | 2 | 10 | 2

## Sheet3 (hidden)
|  |  | No. | Activity | Description | Assumption | Solution Architect | Business Process Consultant | Workflow/Practice Strategist
Plan | 2 | 2 | 1 | Now Assist Agentic AI Workshop |  |  | 4 | 4 | 4 | 12
Plan | 2 | 2 | 2 | Use Case Development |  | Time based, implementation is limited to up to 3 use cases | 4 | 4 | 4 | 12
Plan | 2 | 2 | 3 | Story Development and Review |  |  | 5 | 10 |  | 15
Plan | 2 | 2 | 4 | Business Process Map Workshop (Use-Case Based) |  | Limited to the single use case identified from Use Case Dev above |  | 4 | 4 | 8
Plan | 2 | 2 | 5 | Boeing AI Roadmap Maturation Workshops | Review and update existing customer AI roadmap, including integration recommendations for 3rd party systems (moveworks for example) |  | 8 | 8 | 10 | 26
Plan | 2 | 2 | 6 | Value Realization Dashboard Workshop | Value realization dashboard use case development in support of AI Roadmap |  | 4 | 4 | 8 | 16
Plan | 2 | 2 | 7 | Integrations Evaluation and Recommendations Workshop | Review of existing Boeing 3rd party systems, such as Moveworks, and develop integration recommendations |  | 4 | 4 | 4 | 12
Plan | 2 | 2 | 8 | AI Governance Memo | Governance framework memo for AI | deliverable | 2 | 2 | 2 | 6

## Project Plans
1. Now Assist POC
A. SOW | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
| Date | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22
Initiate
Plan
Execute
Deliver
Close
Option 1 | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
| Date | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22
Initiate
Plan
Execute
Deliver
Close
B. Final Plan Post Workshops | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11
| Start Date | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12
Initiate | bar: 2025-10-27
Plan | bar: 2025-11-03 to 2025-11-17
Execute | bar: 2025-11-24 to 2025-12-15
Deliver | bar: 2025-12-22 to 2026-01-05
Close | bar: 2026-01-12
2. DPR Advisory Services
A. SOW | Week # | 2025-10-27: 1; 2025-11-03: 2; 2025-11-10: 3; 2025-11-17: 4; 2025-11-24: 5; 2025-12-01: 6; 2025-12-08: 7
| Date | 2025-10-27: 2025-11-03; 2025-11-03: 2025-11-10; 2025-11-10: 2025-11-17; 2025-11-17: 2025-11-24; 2025-11-24: 2025-12-01; 2025-12-01: 2025-12-08; 2025-12-08: 2025-12-15
Initiate | bar: 2025-10-27
Plan | bar: 2025-11-03 to 2025-11-24
Close | bar: 2025-12-01
Option 1 | Week # | 2025-10-27: 1; 2025-11-03: 2; 2025-11-10: 3; 2025-11-17: 4; 2025-11-24: 5; 2025-12-01: 6; 2025-12-08: 7
| Date | 2025-10-27: 2025-10-27; 2025-11-03: 2025-11-03; 2025-11-10: 2025-11-10; 2025-11-17: 2025-11-17; 2025-11-24: 2025-11-24; 2025-12-01: 2025-12-01; 2025-12-08: 2025-12-08
Initiate | bar: 2025-10-27
Plan | bar: 2025-11-03 to 2025-11-10
Execute | bar: 2025-11-17 to 2025-12-01
Deliver | bar: 2025-12-08
Close
B. Final Plan Post Workshops | Week # | 2025-10-27: 1; 2025-11-03: 2; 2025-11-10: 3; 2025-11-17: 4; 2025-11-24: 5; 2025-12-01: 6; 2025-12-08: 7
| Week Date | 2025-10-27: 2025-11-03; 2025-11-03: 2025-11-10; 2025-11-10: 2025-11-17; 2025-11-17: 2025-11-24; 2025-11-24: 2025-12-01; 2025-12-01: 2025-12-08; 2025-12-08: 2025-12-15
Initiate | bar: 2025-10-27
Plan | bar: 2025-11-03 to 2025-12-01
Close | bar: 2025-12-08

## Scope Review
Story # | Story Summary | Boeing Roadmap Alignment | SOW Fit | Risk Level | Success Criteria (POC Only) | NR Capabilities
7262098 | Enable Now Assist Panel | Phase 1 – Foundational | ✔ In Scope | Low | Panel accessible, OOB features only, no production rollout
7254011 | Install Now Assist for ITSM | Phase 1 – Foundational | ✔ In Scope | Low | Plugin installed in non-prod, features available to activate
7262101 | Chat Summarization Skill | Phase 1 – Summarization | ✔ In Scope | Medium | Summaries show in UI; accuracy not required; formatting minimal
7262103 | Major Incident Summary | Phase 2 – MIM Comms / Proactive Ops | ❌ Out of Scope | High | Demo-only summary; not matched to Boeing template; roadmap item | Adding fields to LookUP / MIM team's exact use case needed
7262104 | Install Elara/Phoebe | Phase 1 – Authoring Support (Demo) | ✔ In Scope (activation only) | Medium | Agents activated; OOB demo flows only; no Boeing-specific logic
7262114 | Elara Structured KM Use Cases | Phase 3 – Automated KB Mgmt | ❌ Out of Scope | High | Demo-only article draft; no metadata, no approvals, no templates | Meeting tomorrow (26/11)
7262116 | Phoebe Incident Use Cases | Phase 3–4 – Triage, Routing, Auto-Resolution | ❌ Out of Scope | Very High | Demo-only guidance; no state changes, no close automation; roadmap | Meeting tomorrow (26/11)
7262119 | Now Assist Guardian | Phase 1 – Foundations | ✔ In Scope | Low | Offensiveness + PI guardrails enabled; no enterprise policy validation
New Skill | Sentiment Analysis | Phase 2–3 – Analytics + Trend Analysis | ❌ Out of Scope | High | Mock/demo value only; no ML accuracy; no workflow; roadmap | Level of customization required and can be done by project team; detailed steps are included in the stories